## Overview
守織 SHUORI · Workbook overview
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
Snapshot export. User accounts, passwords, sessions and audit logs are excluded. This workbook is not a restorable workspace backup. Dates and times are Japan Standard Time.
Worksheet | Data rows | Contents and interpretation
Project plan summary | 4 | Operational data in the selected scope.
Projects | 1 | Operational data in the selected scope.
Tasks and CPM | 6 | CPM uses the complete project graph, even when task rows are filtered. Day zero is project start; durations include weekends and holidays. Progress does not alter planned duration.
Task dependencies | 6 | Operational data in the selected scope.
Shifts | 39 | Times are Japan Standard Time. Counts describe scheduled assignments, not attendance or live location. Cancelled and draft shifts retain their recorded status.
Assignment roster | 60 | One row per volunteer/shift assignment. Historical completed or cancelled shifts are preserved without applying current readiness retroactively.

## Project plan summary
守織 SHUORI · Project plan summary
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Metric | Value | Definition
Project | A warmer first visit | project-welcome
Planned duration (days) | 19 | Longest finish-to-start dependency path in calendar days.
Critical tasks | 5 | All zero-float tasks, including tied branches.
One critical path | Observe arrival demand → Confirm department routes → Prepare accessible guidance cards → Run the welcome pilot → Review feedback and report | One connected longest path; not all tied critical paths.

## Projects
守織 SHUORI · Projects
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Record ID | Title | Category | Purpose and approach | Owner | Department | Status | Start date | Due date | Budget (JPY) | Spent (JPY) | Budget remaining (JPY) | Goals | Risks | Version | Created (JST) | Updated (JST)
project-welcome | A warmer first visit | Patient experience | Improve the arrival experience through consistent greeting, accessible routes and volunteer support. | Operations team | Medical Administration | active | 2026-09-28 | 2026-10-29 | 90000 | 32000 | 58000 | Pilot an accessible welcome service. Gather anonymous feedback and publish the monthly service report. | Peak-hour demand; changing clinic routes. Confirm all guidance with the department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57

## Tasks and CPM
守織 SHUORI · Tasks and CPM
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
CPM uses the complete project graph, even when task rows are filtered. Day zero is project start; durations include weekends and holidays. Progress does not alter planned duration.
Record ID | Project ID | Project | Title | Duration (calendar days) | Predecessor IDs | Predecessor tasks | Status | Owner | Progress | Earliest start day | Earliest finish day | Latest start day | Latest finish day | Float (days) | Critical task | Version | Created (JST) | Updated (JST)
welcome-1 | project-welcome | A warmer first visit | Observe arrival demand | 3 |  |  | done | Volunteer coordinator | 100% | 0 | 3 | 0 | 3 | 0 | TRUE | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
welcome-2 | project-welcome | A warmer first visit | Confirm department routes | 4 | welcome-1 | Observe arrival demand | done | Volunteer coordinator | 100% | 3 | 7 | 3 | 7 | 0 | TRUE | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
welcome-3 | project-welcome | A warmer first visit | Prepare accessible guidance cards | 5 | welcome-2 | Confirm department routes | doing | Volunteer coordinator | 60% | 7 | 12 | 7 | 12 | 0 | TRUE | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
welcome-4 | project-welcome | A warmer first visit | Brief the pilot team | 2 | welcome-2 | Confirm department routes | todo | Volunteer coordinator | 0% | 7 | 9 | 10 | 12 | 3 | FALSE | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
welcome-5 | project-welcome | A warmer first visit | Run the welcome pilot | 5 | welcome-3 welcome-4 | Prepare accessible guidance cards Brief the pilot team | todo | Volunteer coordinator | 0% | 12 | 17 | 12 | 17 | 0 | TRUE | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
welcome-6 | project-welcome | A warmer first visit | Review feedback and report | 2 | welcome-5 | Run the welcome pilot | todo | Volunteer coordinator | 0% | 17 | 19 | 17 | 19 | 0 | TRUE | 1 | 2026-10-08 16:57 | 2026-10-08 16:57

## Task dependencies
守織 SHUORI · Task dependencies
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Task ID | Task | Predecessor ID | Predecessor task
welcome-2 | Confirm department routes | welcome-1 | Observe arrival demand
welcome-3 | Prepare accessible guidance cards | welcome-2 | Confirm department routes
welcome-4 | Brief the pilot team | welcome-2 | Confirm department routes
welcome-5 | Run the welcome pilot | welcome-3 | Prepare accessible guidance cards
welcome-5 | Run the welcome pilot | welcome-4 | Brief the pilot team
welcome-6 | Review feedback and report | welcome-5 | Run the welcome pilot

## Shifts
守織 SHUORI · Shifts
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
Times are Japan Standard Time. Counts describe scheduled assignments, not attendance or live location. Cancelled and draft shifts retain their recorded status.
Record ID | Title | Date | Start (JST) | End (JST) | Location ID | Service location | Floor | Required skills | Required people | Assigned people | Unfilled positions | Shift hours | Status | Project ID | Project | Administrative notes | Version | Created (JST) | Updated (JST)
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-28-guidance | Outpatient guidance | 2026-09-28 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-28-afternoon | Afternoon reception | 2026-09-28 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-29-guidance | Outpatient guidance | 2026-09-29 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-29-afternoon | Afternoon reception | 2026-09-29 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-30-guidance | Outpatient guidance | 2026-09-30 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-09-30-afternoon | Afternoon reception | 2026-09-30 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-01-guidance | Outpatient guidance | 2026-10-01 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-01-afternoon | Afternoon reception | 2026-10-01 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-02-guidance | Outpatient guidance | 2026-10-02 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-02-afternoon | Afternoon reception | 2026-10-02 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-05-guidance | Outpatient guidance | 2026-10-05 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-05-afternoon | Afternoon reception | 2026-10-05 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-06-guidance | Outpatient guidance | 2026-10-06 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-06-afternoon | Afternoon reception | 2026-10-06 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-07-guidance | Outpatient guidance | 2026-10-07 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-07-afternoon | Afternoon reception | 2026-10-07 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-08-welcome | Morning welcome | 2026-10-08 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 2 | 1 | 3 | confirmed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-08-guidance | Outpatient guidance | 2026-10-08 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 1 | 1 | 2.5 | confirmed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-08-afternoon | Afternoon reception | 2026-10-08 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 1 | 1 | 2 | confirmed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-09-welcome | Morning welcome | 2026-10-09 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-09-guidance | Outpatient guidance | 2026-10-09 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-09-afternoon | Afternoon reception | 2026-10-09 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-12-welcome | Morning welcome | 2026-10-12 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-12-guidance | Outpatient guidance | 2026-10-12 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-12-afternoon | Afternoon reception | 2026-10-12 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-13-welcome | Morning welcome | 2026-10-13 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-13-guidance | Outpatient guidance | 2026-10-13 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-13-afternoon | Afternoon reception | 2026-10-13 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-14-welcome | Morning welcome | 2026-10-14 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-14-guidance | Outpatient guidance | 2026-10-14 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57
shift-2026-10-14-afternoon | Afternoon reception | 2026-10-14 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 16:57 | 2026-10-08 16:57

## Assignment roster
守織 SHUORI · Assignment roster
Generated 2026-10-08 17:07:03 JST · Asia/Tokyo · demo · version 1.3.0
project-plan ¦ All records in the stated scope ¦ Project: project-welcome ¦ View label: Complete plan ¦ tasks & critical path
One row per volunteer/shift assignment. Historical completed or cancelled shifts are preserved without applying current readiness retroactively.
Shift ID | Shift | Date | Start (JST) | End (JST) | Volunteer ID | Volunteer | Location ID | Service location | Floor | Shift status | Scheduled person-hours | Current eligibility check | Review reasons
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | vol-7 | Yuki Nakamura | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | vol-8 | Sofia Garcia | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | vol-9 | Ren Ito | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-28-guidance | Outpatient guidance | 2026-09-28 | 9:30 | 12:00 | vol-10 | Hana Kobayashi | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-28-guidance | Outpatient guidance | 2026-09-28 | 9:30 | 12:00 | vol-11 | Oliver Park | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-28-afternoon | Afternoon reception | 2026-09-28 | 13:00 | 15:00 | vol-1 | Aiko Tanaka | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-28-afternoon | Afternoon reception | 2026-09-28 | 13:00 | 15:00 | vol-2 | Daniel Kim | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | vol-4 | Haruto Suzuki | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | vol-5 | Maya Chen | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | vol-6 | Kenji Mori | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-29-guidance | Outpatient guidance | 2026-09-29 | 9:30 | 12:00 | vol-7 | Yuki Nakamura | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-29-guidance | Outpatient guidance | 2026-09-29 | 9:30 | 12:00 | vol-8 | Sofia Garcia | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-29-afternoon | Afternoon reception | 2026-09-29 | 13:00 | 15:00 | vol-10 | Hana Kobayashi | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-29-afternoon | Afternoon reception | 2026-09-29 | 13:00 | 15:00 | vol-11 | Oliver Park | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | vol-1 | Aiko Tanaka | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | vol-2 | Daniel Kim | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | vol-3 | Emi Sato | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-30-guidance | Outpatient guidance | 2026-09-30 | 9:30 | 12:00 | vol-4 | Haruto Suzuki | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-30-guidance | Outpatient guidance | 2026-09-30 | 9:30 | 12:00 | vol-5 | Maya Chen | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-30-afternoon | Afternoon reception | 2026-09-30 | 13:00 | 15:00 | vol-7 | Yuki Nakamura | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-30-afternoon | Afternoon reception | 2026-09-30 | 13:00 | 15:00 | vol-8 | Sofia Garcia | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | vol-10 | Hana Kobayashi | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | vol-11 | Oliver Park | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | vol-12 | Mei Watanabe | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-01-guidance | Outpatient guidance | 2026-10-01 | 9:30 | 12:00 | vol-1 | Aiko Tanaka | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-01-guidance | Outpatient guidance | 2026-10-01 | 9:30 | 12:00 | vol-2 | Daniel Kim | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-01-afternoon | Afternoon reception | 2026-10-01 | 13:00 | 15:00 | vol-4 | Haruto Suzuki | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-01-afternoon | Afternoon reception | 2026-10-01 | 13:00 | 15:00 | vol-5 | Maya Chen | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | vol-7 | Yuki Nakamura | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | vol-8 | Sofia Garcia | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | vol-9 | Ren Ito | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-02-guidance | Outpatient guidance | 2026-10-02 | 9:30 | 12:00 | vol-10 | Hana Kobayashi | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-02-guidance | Outpatient guidance | 2026-10-02 | 9:30 | 12:00 | vol-11 | Oliver Park | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-02-afternoon | Afternoon reception | 2026-10-02 | 13:00 | 15:00 | vol-1 | Aiko Tanaka | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-02-afternoon | Afternoon reception | 2026-10-02 | 13:00 | 15:00 | vol-2 | Daniel Kim | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | vol-10 | Hana Kobayashi | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | vol-11 | Oliver Park | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | vol-12 | Mei Watanabe | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-05-guidance | Outpatient guidance | 2026-10-05 | 9:30 | 12:00 | vol-1 | Aiko Tanaka | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-05-guidance | Outpatient guidance | 2026-10-05 | 9:30 | 12:00 | vol-2 | Daniel Kim | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-05-afternoon | Afternoon reception | 2026-10-05 | 13:00 | 15:00 | vol-4 | Haruto Suzuki | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-05-afternoon | Afternoon reception | 2026-10-05 | 13:00 | 15:00 | vol-5 | Maya Chen | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | vol-7 | Yuki Nakamura | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | vol-8 | Sofia Garcia | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | vol-9 | Ren Ito | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-06-guidance | Outpatient guidance | 2026-10-06 | 9:30 | 12:00 | vol-10 | Hana Kobayashi | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-06-guidance | Outpatient guidance | 2026-10-06 | 9:30 | 12:00 | vol-11 | Oliver Park | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-06-afternoon | Afternoon reception | 2026-10-06 | 13:00 | 15:00 | vol-1 | Aiko Tanaka | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-06-afternoon | Afternoon reception | 2026-10-06 | 13:00 | 15:00 | vol-2 | Daniel Kim | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | vol-4 | Haruto Suzuki | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | vol-5 | Maya Chen | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | vol-6 | Kenji Mori | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-07-guidance | Outpatient guidance | 2026-10-07 | 9:30 | 12:00 | vol-7 | Yuki Nakamura | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-07-guidance | Outpatient guidance | 2026-10-07 | 9:30 | 12:00 | vol-8 | Sofia Garcia | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-07-afternoon | Afternoon reception | 2026-10-07 | 13:00 | 15:00 | vol-10 | Hana Kobayashi | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-07-afternoon | Afternoon reception | 2026-10-07 | 13:00 | 15:00 | vol-11 | Oliver Park | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-08-welcome | Morning welcome | 2026-10-08 | 9:00 | 12:00 | vol-2 | Daniel Kim | entrance | Main entrance | 1F | confirmed | 3 | Eligible
shift-2026-10-08-welcome | Morning welcome | 2026-10-08 | 9:00 | 12:00 | vol-3 | Emi Sato | entrance | Main entrance | 1F | confirmed | 3 | Eligible
shift-2026-10-08-guidance | Outpatient guidance | 2026-10-08 | 9:30 | 12:00 | vol-4 | Haruto Suzuki | outpatient | Outpatient support | 1F | confirmed | 2.5 | Eligible
shift-2026-10-08-afternoon | Afternoon reception | 2026-10-08 | 13:00 | 15:00 | vol-7 | Yuki Nakamura | reception | Reception & wayfinding | 1F | confirmed | 2 | Eligible