## Overview
守織 SHUORI · Workbook overview
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Snapshot export. User accounts, passwords, sessions and audit logs are excluded. This workbook is not a restorable workspace backup. Dates and times are Japan Standard Time.
Worksheet | Data rows | Contents and interpretation
Volunteers | 18 | Administrative readiness as of 2026-10-08. Actual shift eligibility also depends on skills, availability, workload and conflicts. No clinical findings are modeled.
Projects | 4 | Operational data in the selected scope.
Tasks and CPM | 18 | CPM uses the complete project graph, even when task rows are filtered. Day zero is project start; durations include weekends and holidays. Progress does not alter planned duration.
Task dependencies | 16 | Operational data in the selected scope.
Shifts | 47 | Times are Japan Standard Time. Counts describe scheduled assignments, not attendance or live location. Cancelled and draft shifts retain their recorded status.
Assignment roster | 70 | One row per volunteer/shift assignment. Historical completed or cancelled shifts are preserved without applying current readiness retroactively.
Activity records | 66 | Service interactions are aggregate recorded interactions, not unique patients or visitors.
Support requests | 4 | Operational data in the selected scope.
Resources | 5 | Operational data in the selected scope.
Scenarios | 0 | Spatial studies are independent of the operational roster. Coordinates are illustrative floor-local units.
Scene object overrides | 0 | Operational data in the selected scope.
Scene additions | 0 | Operational data in the selected scope.
Scene routes | 0 | Illustrative floor-local rehearsal. A round trip is 24 simulation minutes; no collision detection, measured walking speed or cross-floor routing.
Route points | 0 | Operational data in the selected scope.
Event types | 4 | Custom event classifications and module defaults. A type does not grant additional access permissions.
Events | 3 | Tokyo civil dates and times. Meeting passcodes and URL query/fragment data are excluded; use the event in SHUORI for its complete join link. Attendance does not create service hours.
Event attendance | 4 | Recorded invitation, confirmation and attendance states. Assigned participants without an attendance entry remain in Event relationships.
Event checklist | 3 | Operational data in the selected scope.
Event relationships | 12 | Explicit links to participants, shifts, resources and project. A resource link is a planning reference, not an inventory reservation.
Journal entries | 2 | Flexible journal and follow-up records. These entries are not counted as service hours; activity records remain the source for hours and interactions.
Files and links | 0 | Metadata only: file bytes, physical storage paths and credentials are excluded. File download paths require a signed-in session on the originating SHUORI installation. External URLs remain literal text and retain their saved query parameters.
Locations | 6 | Coordinates and capacity are illustrative planning assumptions, not surveyed dimensions or approved capacity limits.
Field dictionary | 3 | Custom columns retain stable field IDs, labels and native value types. Archived definitions and existing values remain exportable. An empty selected scope includes headers only.

## Volunteers
守織 SHUORI · Volunteers
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Administrative readiness as of 2026-10-08. Actual shift eligibility also depends on skills, availability, workload and conflicts. No clinical findings are modeled.
Record ID | Volunteer name | Name reading | Email | Phone (text) | Contact preference | Postal address | Emergency contact name | Emergency contact relationship | Emergency contact phone (text) | Profile tags | Programme status | Skills | Languages | Training status | Administrative clearance | Next clearance review | Administratively ready | Available weekdays | Available from | Available until | Weekly hour cap | Joined date | Administrative notes | Preferred contribution [field-preferred-role] | Version | Created (JST) | Updated (JST)
vol-1 | Aiko Tanaka |  | volunteer1@example.invalid |  | email |  |  |  |  | Welcome team | active | Wayfinding Wheelchair support Event support | Japanese English | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 13:00 | 8 | 2026-06-10 | Synthetic demonstration profile. No real volunteer or health information. | Welcome desk | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-2 | Daniel Kim |  | volunteer2@example.invalid |  | email |  |  |  |  | Welcome team | active | Wayfinding Library support Event support | Japanese Korean | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-05-28 | Synthetic demonstration profile. No real volunteer or health information. | Library programme | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-3 | Emi Sato |  | volunteer3@example.invalid |  | email |  |  |  |  | Welcome team | active | Wayfinding Library support | Japanese | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-05-15 | Synthetic demonstration profile. No real volunteer or health information. | Behind the scenes | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-4 | Haruto Suzuki |  | volunteer4@example.invalid |  | email | [5 empty] | active | Wayfinding Wheelchair support Event support | Japanese | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-05-02 | Synthetic demonstration profile. No real volunteer or health information. | Welcome desk | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-5 | Maya Chen |  | volunteer5@example.invalid |  | email | [5 empty] | active | Wayfinding Library support Event support | Japanese English | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 8 | 2026-04-19 | Synthetic demonstration profile. No real volunteer or health information. | Library programme | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-6 | Kenji Mori |  | volunteer6@example.invalid |  | email | [5 empty] | active | Wayfinding Library support | Japanese Korean | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 13:00 | 12 | 2026-04-06 | Synthetic demonstration profile. No real volunteer or health information. | Behind the scenes | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-7 | Yuki Nakamura |  | volunteer7@example.invalid |  | email | [5 empty] | active | Wayfinding Wheelchair support Event support | Japanese | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-03-24 | Synthetic demonstration profile. No real volunteer or health information. | Welcome desk | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-8 | Sofia Garcia |  | volunteer8@example.invalid |  | email | [5 empty] | active | Wayfinding Library support Event support | Japanese | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-03-11 | Synthetic demonstration profile. No real volunteer or health information. | Library programme | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-9 | Ren Ito |  | volunteer9@example.invalid |  | email | [5 empty] | active | Wayfinding Library support | Japanese English | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 8 | 2026-02-26 | Synthetic demonstration profile. No real volunteer or health information. | Behind the scenes | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-10 | Hana Kobayashi |  | volunteer10@example.invalid |  | email | [5 empty] | active | Wayfinding Wheelchair support Event support | Japanese Korean | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-02-13 | Synthetic demonstration profile. No real volunteer or health information. | Welcome desk | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-11 | Oliver Park |  | volunteer11@example.invalid |  | email | [5 empty] | active | Wayfinding Library support Event support | Japanese | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 13:00 | 12 | 2026-01-31 | Synthetic demonstration profile. No real volunteer or health information. | Library programme | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-12 | Mei Watanabe |  | volunteer12@example.invalid |  | email | [5 empty] | active | Wayfinding Library support | Japanese | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri | 8:00 | 17:00 | 12 | 2026-01-18 | Synthetic demonstration profile. No real volunteer or health information. | Behind the scenes | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-13 | Sara Yamamoto |  | volunteer13@example.invalid |  | email | [5 empty] | active | Wayfinding Wheelchair support Event support | Japanese English | complete | cleared | 2026-10-15 | TRUE | mon tue wed thu fri sat sun | 8:00 | 17:00 | 8 | 2026-01-05 | Synthetic demonstration profile. No real volunteer or health information. | Welcome desk | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-14 | Leo Nishida |  | volunteer14@example.invalid |  | email | [5 empty] | active | Wayfinding Library support Event support | Japanese Korean | complete | cleared | 2027-04-06 | TRUE | mon tue wed thu fri sat sun | 8:00 | 17:00 | 12 | 2025-12-23 | Synthetic demonstration profile. No real volunteer or health information. | Library programme | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-15 | Nora Hayashi |  | volunteer15@example.invalid |  | email |  |  |  |  | New intake | onboarding | Wayfinding Library support | Japanese | pending | cleared | 2027-04-06 | FALSE | mon tue wed thu fri sat sun | 8:00 | 17:00 | 12 | 2025-12-10 | Synthetic demonstration profile. No real volunteer or health information. | Behind the scenes | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-16 | Kai Takahashi |  | volunteer16@example.invalid |  | email |  |  |  |  | New intake | applicant | Wayfinding Wheelchair support Event support | Japanese | pending | pending | 2027-04-06 | FALSE | mon tue wed thu fri sat sun | 8:00 | 13:00 | 12 | 2025-11-27 | Synthetic demonstration profile. No real volunteer or health information. | Welcome desk | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-17 | Rina Abe |  | volunteer17@example.invalid |  | email | [5 empty] | paused | Wayfinding Library support Event support | Japanese English | complete | cleared | 2027-04-06 | FALSE | mon tue wed thu fri sat sun | 8:00 | 17:00 | 8 | 2025-11-14 | Synthetic demonstration profile. No real volunteer or health information. | Library programme | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
vol-18 | Theo Matsuda |  | volunteer18@example.invalid |  | email | [5 empty] | active | Wayfinding Library support | Japanese Korean | complete | pending | 2026-10-06 | FALSE | mon tue wed thu fri sat sun | 8:00 | 17:00 | 12 | 2025-11-01 | Synthetic demonstration profile. No real volunteer or health information. | Behind the scenes | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Projects
守織 SHUORI · Projects
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Record ID | Title | Category | Purpose and approach | Owner | Department | Status | Start date | Due date | Budget (JPY) | Spent (JPY) | Budget remaining (JPY) | Goals | Risks | Version | Created (JST) | Updated (JST)
project-welcome | A warmer first visit | Patient experience | Improve the arrival experience through consistent greeting, accessible routes and volunteer support. | Operations team | Medical Administration | active | 2026-09-28 | 2026-10-29 | 90000 | 32000 | 58000 | Pilot an accessible welcome service. Gather anonymous feedback and publish the monthly service report. | Peak-hour demand; changing clinic routes. Confirm all guidance with the department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
project-library | Stories that connect | Library programme | Support the library with a welcoming reading programme and a refreshed circulation workflow. | Library team | Patient Services | planning | 2026-10-05 | 2026-11-12 | 60000 | 8000 | 52000 | Prepare a themed reading shelf and brief volunteers on the library workflow. | Library opening hours and infection-control requirements must be confirmed before activities. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
project-autumn | Autumn appreciation gathering | Events & recognition | Recognise volunteer contributions and share learning across departments at a small approved gathering. | Volunteer office | Medical Administration | approved | 2026-10-01 | 2026-11-05 | 120000 | 18500 | 101500 | Recognise participation and prepare a clear, inclusive event run sheet. | Venue availability and hospital approval. The courtyard zone is a planning concept. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
project-onboarding | Ready to help: orientation | Recruitment & training | Coordinate recruitment, interviews, training and administrative health-clearance reminders for the next volunteer intake. | Volunteer coordinator | Medical Administration | active | 2026-09-24 | 2026-10-22 | 30000 | 12000 | 18000 | Complete orientation and administrative checks before assigning new volunteers. | Do not record medical details here. Clearance decisions belong to authorised hospital staff. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Tasks and CPM
守織 SHUORI · Tasks and CPM
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
CPM uses the complete project graph, even when task rows are filtered. Day zero is project start; durations include weekends and holidays. Progress does not alter planned duration.
Record ID | Project ID | Project | Title | Duration (calendar days) | Predecessor IDs | Predecessor tasks | Status | Owner | Progress | Earliest start day | Earliest finish day | Latest start day | Latest finish day | Float (days) | Critical task | Version | Created (JST) | Updated (JST)
welcome-1 | project-welcome | A warmer first visit | Observe arrival demand | 3 |  |  | done | Volunteer coordinator | 100% | 0 | 3 | 0 | 3 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
welcome-2 | project-welcome | A warmer first visit | Confirm department routes | 4 | welcome-1 | Observe arrival demand | done | Volunteer coordinator | 100% | 3 | 7 | 3 | 7 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
welcome-3 | project-welcome | A warmer first visit | Prepare accessible guidance cards | 5 | welcome-2 | Confirm department routes | doing | Volunteer coordinator | 60% | 7 | 12 | 7 | 12 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
welcome-4 | project-welcome | A warmer first visit | Brief the pilot team | 2 | welcome-2 | Confirm department routes | todo | Volunteer coordinator | 0% | 7 | 9 | 10 | 12 | 3 | FALSE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
welcome-5 | project-welcome | A warmer first visit | Run the welcome pilot | 5 | welcome-3 welcome-4 | Prepare accessible guidance cards Brief the pilot team | todo | Volunteer coordinator | 0% | 12 | 17 | 12 | 17 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
welcome-6 | project-welcome | A warmer first visit | Review feedback and report | 2 | welcome-5 | Run the welcome pilot | todo | Volunteer coordinator | 0% | 17 | 19 | 17 | 19 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
library-1 | project-library | Stories that connect | Agree programme with library staff | 3 |  |  | doing | Volunteer coordinator | 40% | 0 | 3 | 0 | 3 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
library-2 | project-library | Stories that connect | Select themed reading collection | 5 | library-1 | Agree programme with library staff | todo | Volunteer coordinator | 0% | 3 | 8 | 3 | 8 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
library-3 | project-library | Stories that connect | Prepare circulation briefing | 2 | library-1 | Agree programme with library staff | todo | Volunteer coordinator | 0% | 3 | 5 | 6 | 8 | 3 | FALSE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
library-4 | project-library | Stories that connect | Launch reading programme | 2 | library-2 library-3 | Select themed reading collection Prepare circulation briefing | todo | Volunteer coordinator | 0% | 8 | 10 | 8 | 10 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
autumn-1 | project-autumn | Autumn appreciation gathering | Confirm venue and approvals | 4 |  |  | doing | Volunteer coordinator | 50% | 0 | 4 | 0 | 4 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
autumn-2 | project-autumn | Autumn appreciation gathering | Draft recognition list | 3 |  |  | done | Volunteer coordinator | 100% | 0 | 3 | 1 | 4 | 1 | FALSE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
autumn-3 | project-autumn | Autumn appreciation gathering | Prepare event run sheet | 3 | autumn-1 autumn-2 | Confirm venue and approvals Draft recognition list | todo | Volunteer coordinator | 0% | 4 | 7 | 4 | 7 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
autumn-4 | project-autumn | Autumn appreciation gathering | Volunteer appreciation event | 1 | autumn-3 | Prepare event run sheet | todo | Volunteer coordinator | 0% | 7 | 8 | 7 | 8 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
onboarding-1 | project-onboarding | Ready to help: orientation | Publish recruitment information | 2 |  |  | done | Volunteer coordinator | 100% | 0 | 2 | 0 | 2 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
onboarding-2 | project-onboarding | Ready to help: orientation | Coordinate intake conversations | 4 | onboarding-1 | Publish recruitment information | done | Volunteer coordinator | 100% | 2 | 6 | 2 | 6 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
onboarding-3 | project-onboarding | Ready to help: orientation | Complete orientation and reminders | 5 | onboarding-2 | Coordinate intake conversations | doing | Volunteer coordinator | 70% | 6 | 11 | 6 | 11 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
onboarding-4 | project-onboarding | Ready to help: orientation | Review readiness and first assignments | 2 | onboarding-3 | Complete orientation and reminders | todo | Volunteer coordinator | 0% | 11 | 13 | 11 | 13 | 0 | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Task dependencies
守織 SHUORI · Task dependencies
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Task ID | Task | Predecessor ID | Predecessor task
welcome-2 | Confirm department routes | welcome-1 | Observe arrival demand
welcome-3 | Prepare accessible guidance cards | welcome-2 | Confirm department routes
welcome-4 | Brief the pilot team | welcome-2 | Confirm department routes
welcome-5 | Run the welcome pilot | welcome-3 | Prepare accessible guidance cards
welcome-5 | Run the welcome pilot | welcome-4 | Brief the pilot team
welcome-6 | Review feedback and report | welcome-5 | Run the welcome pilot
library-2 | Select themed reading collection | library-1 | Agree programme with library staff
library-3 | Prepare circulation briefing | library-1 | Agree programme with library staff
library-4 | Launch reading programme | library-2 | Select themed reading collection
library-4 | Launch reading programme | library-3 | Prepare circulation briefing
autumn-3 | Prepare event run sheet | autumn-1 | Confirm venue and approvals
autumn-3 | Prepare event run sheet | autumn-2 | Draft recognition list
autumn-4 | Volunteer appreciation event | autumn-3 | Prepare event run sheet
onboarding-2 | Coordinate intake conversations | onboarding-1 | Publish recruitment information
onboarding-3 | Complete orientation and reminders | onboarding-2 | Coordinate intake conversations
onboarding-4 | Review readiness and first assignments | onboarding-3 | Complete orientation and reminders

## Shifts
守織 SHUORI · Shifts
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Times are Japan Standard Time. Counts describe scheduled assignments, not attendance or live location. Cancelled and draft shifts retain their recorded status.
Record ID | Title | Date | Start (JST) | End (JST) | Location ID | Service location | Floor | Required skills | Required people | Assigned people | Unfilled positions | Shift hours | Status | Project ID | Project | Administrative notes | Version | Created (JST) | Updated (JST)
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-28-guidance | Outpatient guidance | 2026-09-28 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-28-afternoon | Afternoon reception | 2026-09-28 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-28-library | Library welcome | 2026-09-28 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 2 | 0 | 2 | completed | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-29-guidance | Outpatient guidance | 2026-09-29 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-29-afternoon | Afternoon reception | 2026-09-29 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-30-guidance | Outpatient guidance | 2026-09-30 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-30-afternoon | Afternoon reception | 2026-09-30 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-09-30-library | Library welcome | 2026-09-30 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 2 | 0 | 2 | completed | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-01-guidance | Outpatient guidance | 2026-10-01 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-01-afternoon | Afternoon reception | 2026-10-01 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-02-guidance | Outpatient guidance | 2026-10-02 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-02-afternoon | Afternoon reception | 2026-10-02 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-02-library | Library welcome | 2026-10-02 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 2 | 0 | 2 | completed | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-05-guidance | Outpatient guidance | 2026-10-05 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-05-afternoon | Afternoon reception | 2026-10-05 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-05-library | Library welcome | 2026-10-05 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 2 | 0 | 2 | completed | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-06-guidance | Outpatient guidance | 2026-10-06 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-06-afternoon | Afternoon reception | 2026-10-06 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 3 | 0 | 3 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-07-guidance | Outpatient guidance | 2026-10-07 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 2 | 0 | 2.5 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-07-afternoon | Afternoon reception | 2026-10-07 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 2 | 0 | 2 | completed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-07-library | Library welcome | 2026-10-07 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 2 | 0 | 2 | completed | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-08-welcome | Morning welcome | 2026-10-08 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 2 | 1 | 3 | confirmed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-08-guidance | Outpatient guidance | 2026-10-08 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 1 | 1 | 2.5 | confirmed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-08-afternoon | Afternoon reception | 2026-10-08 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 1 | 1 | 2 | confirmed | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-09-welcome | Morning welcome | 2026-10-09 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-09-guidance | Outpatient guidance | 2026-10-09 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-09-afternoon | Afternoon reception | 2026-10-09 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-09-library | Library welcome | 2026-10-09 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 0 | 2 | 2 | draft | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-12-welcome | Morning welcome | 2026-10-12 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-12-guidance | Outpatient guidance | 2026-10-12 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-12-afternoon | Afternoon reception | 2026-10-12 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-12-library | Library welcome | 2026-10-12 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 0 | 2 | 2 | draft | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-13-welcome | Morning welcome | 2026-10-13 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-13-guidance | Outpatient guidance | 2026-10-13 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-13-afternoon | Afternoon reception | 2026-10-13 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-14-welcome | Morning welcome | 2026-10-14 | 9:00 | 12:00 | entrance | Main entrance | 1F | Wayfinding | 3 | 0 | 3 | 3 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-14-guidance | Outpatient guidance | 2026-10-14 | 9:30 | 12:00 | outpatient | Outpatient support | 1F | Wayfinding | 2 | 0 | 2 | 2.5 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-14-afternoon | Afternoon reception | 2026-10-14 | 13:00 | 15:00 | reception | Reception & wayfinding | 1F | Wayfinding | 2 | 0 | 2 | 2 | draft | project-welcome | A warmer first visit | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
shift-2026-10-14-library | Library welcome | 2026-10-14 | 10:00 | 12:00 | library | Library | 6F | Library support | 2 | 0 | 2 | 2 | draft | project-library | Stories that connect | Synthetic planning data. Confirm operational arrangements with the relevant department. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Assignment roster
守織 SHUORI · Assignment roster
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
One row per volunteer/shift assignment. Historical completed or cancelled shifts are preserved without applying current readiness retroactively.
Shift ID | Shift | Date | Start (JST) | End (JST) | Volunteer ID | Volunteer | Location ID | Service location | Floor | Shift status | Scheduled person-hours | Current eligibility check | Review reasons
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | vol-7 | Yuki Nakamura | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | vol-8 | Sofia Garcia | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-28-welcome | Morning welcome | 2026-09-28 | 9:00 | 12:00 | vol-9 | Ren Ito | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-28-guidance | Outpatient guidance | 2026-09-28 | 9:30 | 12:00 | vol-10 | Hana Kobayashi | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-28-guidance | Outpatient guidance | 2026-09-28 | 9:30 | 12:00 | vol-11 | Oliver Park | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-28-afternoon | Afternoon reception | 2026-09-28 | 13:00 | 15:00 | vol-1 | Aiko Tanaka | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-28-afternoon | Afternoon reception | 2026-09-28 | 13:00 | 15:00 | vol-2 | Daniel Kim | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-28-library | Library welcome | 2026-09-28 | 10:00 | 12:00 | vol-3 | Emi Sato | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-09-28-library | Library welcome | 2026-09-28 | 10:00 | 12:00 | vol-4 | Haruto Suzuki | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | vol-4 | Haruto Suzuki | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | vol-5 | Maya Chen | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-29-welcome | Morning welcome | 2026-09-29 | 9:00 | 12:00 | vol-6 | Kenji Mori | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-29-guidance | Outpatient guidance | 2026-09-29 | 9:30 | 12:00 | vol-7 | Yuki Nakamura | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-29-guidance | Outpatient guidance | 2026-09-29 | 9:30 | 12:00 | vol-8 | Sofia Garcia | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-29-afternoon | Afternoon reception | 2026-09-29 | 13:00 | 15:00 | vol-10 | Hana Kobayashi | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-29-afternoon | Afternoon reception | 2026-09-29 | 13:00 | 15:00 | vol-11 | Oliver Park | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | vol-1 | Aiko Tanaka | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | vol-2 | Daniel Kim | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-30-welcome | Morning welcome | 2026-09-30 | 9:00 | 12:00 | vol-3 | Emi Sato | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-09-30-guidance | Outpatient guidance | 2026-09-30 | 9:30 | 12:00 | vol-4 | Haruto Suzuki | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-30-guidance | Outpatient guidance | 2026-09-30 | 9:30 | 12:00 | vol-5 | Maya Chen | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-09-30-afternoon | Afternoon reception | 2026-09-30 | 13:00 | 15:00 | vol-7 | Yuki Nakamura | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-30-afternoon | Afternoon reception | 2026-09-30 | 13:00 | 15:00 | vol-8 | Sofia Garcia | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-09-30-library | Library welcome | 2026-09-30 | 10:00 | 12:00 | vol-9 | Ren Ito | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-09-30-library | Library welcome | 2026-09-30 | 10:00 | 12:00 | vol-10 | Hana Kobayashi | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | vol-10 | Hana Kobayashi | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | vol-11 | Oliver Park | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-01-welcome | Morning welcome | 2026-10-01 | 9:00 | 12:00 | vol-12 | Mei Watanabe | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-01-guidance | Outpatient guidance | 2026-10-01 | 9:30 | 12:00 | vol-1 | Aiko Tanaka | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-01-guidance | Outpatient guidance | 2026-10-01 | 9:30 | 12:00 | vol-2 | Daniel Kim | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-01-afternoon | Afternoon reception | 2026-10-01 | 13:00 | 15:00 | vol-4 | Haruto Suzuki | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-01-afternoon | Afternoon reception | 2026-10-01 | 13:00 | 15:00 | vol-5 | Maya Chen | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | vol-7 | Yuki Nakamura | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | vol-8 | Sofia Garcia | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-02-welcome | Morning welcome | 2026-10-02 | 9:00 | 12:00 | vol-9 | Ren Ito | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-02-guidance | Outpatient guidance | 2026-10-02 | 9:30 | 12:00 | vol-10 | Hana Kobayashi | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-02-guidance | Outpatient guidance | 2026-10-02 | 9:30 | 12:00 | vol-11 | Oliver Park | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-02-afternoon | Afternoon reception | 2026-10-02 | 13:00 | 15:00 | vol-1 | Aiko Tanaka | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-02-afternoon | Afternoon reception | 2026-10-02 | 13:00 | 15:00 | vol-2 | Daniel Kim | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-02-library | Library welcome | 2026-10-02 | 10:00 | 12:00 | vol-3 | Emi Sato | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-02-library | Library welcome | 2026-10-02 | 10:00 | 12:00 | vol-4 | Haruto Suzuki | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | vol-10 | Hana Kobayashi | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | vol-11 | Oliver Park | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-05-welcome | Morning welcome | 2026-10-05 | 9:00 | 12:00 | vol-12 | Mei Watanabe | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-05-guidance | Outpatient guidance | 2026-10-05 | 9:30 | 12:00 | vol-1 | Aiko Tanaka | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-05-guidance | Outpatient guidance | 2026-10-05 | 9:30 | 12:00 | vol-2 | Daniel Kim | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-05-afternoon | Afternoon reception | 2026-10-05 | 13:00 | 15:00 | vol-4 | Haruto Suzuki | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-05-afternoon | Afternoon reception | 2026-10-05 | 13:00 | 15:00 | vol-5 | Maya Chen | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-05-library | Library welcome | 2026-10-05 | 10:00 | 12:00 | vol-6 | Kenji Mori | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-05-library | Library welcome | 2026-10-05 | 10:00 | 12:00 | vol-7 | Yuki Nakamura | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | vol-7 | Yuki Nakamura | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | vol-8 | Sofia Garcia | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-06-welcome | Morning welcome | 2026-10-06 | 9:00 | 12:00 | vol-9 | Ren Ito | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-06-guidance | Outpatient guidance | 2026-10-06 | 9:30 | 12:00 | vol-10 | Hana Kobayashi | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-06-guidance | Outpatient guidance | 2026-10-06 | 9:30 | 12:00 | vol-11 | Oliver Park | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-06-afternoon | Afternoon reception | 2026-10-06 | 13:00 | 15:00 | vol-1 | Aiko Tanaka | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-06-afternoon | Afternoon reception | 2026-10-06 | 13:00 | 15:00 | vol-2 | Daniel Kim | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | vol-4 | Haruto Suzuki | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | vol-5 | Maya Chen | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-07-welcome | Morning welcome | 2026-10-07 | 9:00 | 12:00 | vol-6 | Kenji Mori | entrance | Main entrance | 1F | completed | 3 | Historical; not reassessed
shift-2026-10-07-guidance | Outpatient guidance | 2026-10-07 | 9:30 | 12:00 | vol-7 | Yuki Nakamura | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-07-guidance | Outpatient guidance | 2026-10-07 | 9:30 | 12:00 | vol-8 | Sofia Garcia | outpatient | Outpatient support | 1F | completed | 2.5 | Historical; not reassessed
shift-2026-10-07-afternoon | Afternoon reception | 2026-10-07 | 13:00 | 15:00 | vol-10 | Hana Kobayashi | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-07-afternoon | Afternoon reception | 2026-10-07 | 13:00 | 15:00 | vol-11 | Oliver Park | reception | Reception & wayfinding | 1F | completed | 2 | Historical; not reassessed
shift-2026-10-07-library | Library welcome | 2026-10-07 | 10:00 | 12:00 | vol-12 | Mei Watanabe | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-07-library | Library welcome | 2026-10-07 | 10:00 | 12:00 | vol-1 | Aiko Tanaka | library | Library | 6F | completed | 2 | Historical; not reassessed
shift-2026-10-08-welcome | Morning welcome | 2026-10-08 | 9:00 | 12:00 | vol-2 | Daniel Kim | entrance | Main entrance | 1F | confirmed | 3 | Eligible
shift-2026-10-08-welcome | Morning welcome | 2026-10-08 | 9:00 | 12:00 | vol-3 | Emi Sato | entrance | Main entrance | 1F | confirmed | 3 | Eligible
shift-2026-10-08-guidance | Outpatient guidance | 2026-10-08 | 9:30 | 12:00 | vol-4 | Haruto Suzuki | outpatient | Outpatient support | 1F | confirmed | 2.5 | Eligible
shift-2026-10-08-afternoon | Afternoon reception | 2026-10-08 | 13:00 | 15:00 | vol-7 | Yuki Nakamura | reception | Reception & wayfinding | 1F | confirmed | 2 | Eligible

## Activity records
守織 SHUORI · Activity records
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Service interactions are aggregate recorded interactions, not unique patients or visitors.
Record ID | Volunteer ID | Volunteer | Shift ID | Shift | Event ID | Event | Date | Recorded hours | Service interactions | Service category | Administrative notes | Version | Created (JST) | Updated (JST)
record-2026-09-28-welcome-0 | vol-7 | Yuki Nakamura | shift-2026-09-28-welcome | Morning welcome |  |  | 2026-09-28 | 3 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-welcome-1 | vol-8 | Sofia Garcia | shift-2026-09-28-welcome | Morning welcome |  |  | 2026-09-28 | 3 | 23 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-welcome-2 | vol-9 | Ren Ito | shift-2026-09-28-welcome | Morning welcome |  |  | 2026-09-28 | 3 | 12 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-guidance-0 | vol-10 | Hana Kobayashi | shift-2026-09-28-guidance | Outpatient guidance |  |  | 2026-09-28 | 2.5 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-guidance-1 | vol-11 | Oliver Park | shift-2026-09-28-guidance | Outpatient guidance |  |  | 2026-09-28 | 2.5 | 23 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-afternoon-0 | vol-1 | Aiko Tanaka | shift-2026-09-28-afternoon | Afternoon reception |  |  | 2026-09-28 | 2 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-afternoon-1 | vol-2 | Daniel Kim | shift-2026-09-28-afternoon | Afternoon reception |  |  | 2026-09-28 | 2 | 23 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-library-0 | vol-3 | Emi Sato | shift-2026-09-28-library | Library welcome |  |  | 2026-09-28 | 2 | 22 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-28-library-1 | vol-4 | Haruto Suzuki | shift-2026-09-28-library | Library welcome |  |  | 2026-09-28 | 2 | 23 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-welcome-0 | vol-4 | Haruto Suzuki | shift-2026-09-29-welcome | Morning welcome |  |  | 2026-09-29 | 3 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-welcome-1 | vol-5 | Maya Chen | shift-2026-09-29-welcome | Morning welcome |  |  | 2026-09-29 | 3 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-welcome-2 | vol-6 | Kenji Mori | shift-2026-09-29-welcome | Morning welcome |  |  | 2026-09-29 | 3 | 23 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-guidance-0 | vol-7 | Yuki Nakamura | shift-2026-09-29-guidance | Outpatient guidance |  |  | 2026-09-29 | 2.5 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-guidance-1 | vol-8 | Sofia Garcia | shift-2026-09-29-guidance | Outpatient guidance |  |  | 2026-09-29 | 2.5 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-afternoon-0 | vol-10 | Hana Kobayashi | shift-2026-09-29-afternoon | Afternoon reception |  |  | 2026-09-29 | 2 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-29-afternoon-1 | vol-11 | Oliver Park | shift-2026-09-29-afternoon | Afternoon reception |  |  | 2026-09-29 | 2 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-welcome-0 | vol-1 | Aiko Tanaka | shift-2026-09-30-welcome | Morning welcome |  |  | 2026-09-30 | 3 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-welcome-1 | vol-2 | Daniel Kim | shift-2026-09-30-welcome | Morning welcome |  |  | 2026-09-30 | 3 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-welcome-2 | vol-3 | Emi Sato | shift-2026-09-30-welcome | Morning welcome |  |  | 2026-09-30 | 3 | 22 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-guidance-0 | vol-4 | Haruto Suzuki | shift-2026-09-30-guidance | Outpatient guidance |  |  | 2026-09-30 | 2.5 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-guidance-1 | vol-5 | Maya Chen | shift-2026-09-30-guidance | Outpatient guidance |  |  | 2026-09-30 | 2.5 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-afternoon-0 | vol-7 | Yuki Nakamura | shift-2026-09-30-afternoon | Afternoon reception |  |  | 2026-09-30 | 2 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-afternoon-1 | vol-8 | Sofia Garcia | shift-2026-09-30-afternoon | Afternoon reception |  |  | 2026-09-30 | 2 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-library-0 | vol-9 | Ren Ito | shift-2026-09-30-library | Library welcome |  |  | 2026-09-30 | 2 | 20 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-09-30-library-1 | vol-10 | Hana Kobayashi | shift-2026-09-30-library | Library welcome |  |  | 2026-09-30 | 2 | 21 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-welcome-0 | vol-10 | Hana Kobayashi | shift-2026-10-01-welcome | Morning welcome |  |  | 2026-10-01 | 3 | 19 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-welcome-1 | vol-11 | Oliver Park | shift-2026-10-01-welcome | Morning welcome |  |  | 2026-10-01 | 3 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-welcome-2 | vol-12 | Mei Watanabe | shift-2026-10-01-welcome | Morning welcome |  |  | 2026-10-01 | 3 | 21 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-guidance-0 | vol-1 | Aiko Tanaka | shift-2026-10-01-guidance | Outpatient guidance |  |  | 2026-10-01 | 2.5 | 19 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-guidance-1 | vol-2 | Daniel Kim | shift-2026-10-01-guidance | Outpatient guidance |  |  | 2026-10-01 | 2.5 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-afternoon-0 | vol-4 | Haruto Suzuki | shift-2026-10-01-afternoon | Afternoon reception |  |  | 2026-10-01 | 2 | 19 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-01-afternoon-1 | vol-5 | Maya Chen | shift-2026-10-01-afternoon | Afternoon reception |  |  | 2026-10-01 | 2 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-welcome-0 | vol-7 | Yuki Nakamura | shift-2026-10-02-welcome | Morning welcome |  |  | 2026-10-02 | 3 | 18 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-welcome-1 | vol-8 | Sofia Garcia | shift-2026-10-02-welcome | Morning welcome |  |  | 2026-10-02 | 3 | 19 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-welcome-2 | vol-9 | Ren Ito | shift-2026-10-02-welcome | Morning welcome |  |  | 2026-10-02 | 3 | 20 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-guidance-0 | vol-10 | Hana Kobayashi | shift-2026-10-02-guidance | Outpatient guidance |  |  | 2026-10-02 | 2.5 | 18 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-guidance-1 | vol-11 | Oliver Park | shift-2026-10-02-guidance | Outpatient guidance |  |  | 2026-10-02 | 2.5 | 19 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-afternoon-0 | vol-1 | Aiko Tanaka | shift-2026-10-02-afternoon | Afternoon reception |  |  | 2026-10-02 | 2 | 18 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-afternoon-1 | vol-2 | Daniel Kim | shift-2026-10-02-afternoon | Afternoon reception |  |  | 2026-10-02 | 2 | 19 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-library-0 | vol-3 | Emi Sato | shift-2026-10-02-library | Library welcome |  |  | 2026-10-02 | 2 | 18 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-02-library-1 | vol-4 | Haruto Suzuki | shift-2026-10-02-library | Library welcome |  |  | 2026-10-02 | 2 | 19 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-welcome-0 | vol-10 | Hana Kobayashi | shift-2026-10-05-welcome | Morning welcome |  |  | 2026-10-05 | 3 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-welcome-1 | vol-11 | Oliver Park | shift-2026-10-05-welcome | Morning welcome |  |  | 2026-10-05 | 3 | 16 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-welcome-2 | vol-12 | Mei Watanabe | shift-2026-10-05-welcome | Morning welcome |  |  | 2026-10-05 | 3 | 17 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-guidance-0 | vol-1 | Aiko Tanaka | shift-2026-10-05-guidance | Outpatient guidance |  |  | 2026-10-05 | 2.5 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-guidance-1 | vol-2 | Daniel Kim | shift-2026-10-05-guidance | Outpatient guidance |  |  | 2026-10-05 | 2.5 | 16 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-afternoon-0 | vol-4 | Haruto Suzuki | shift-2026-10-05-afternoon | Afternoon reception |  |  | 2026-10-05 | 2 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-afternoon-1 | vol-5 | Maya Chen | shift-2026-10-05-afternoon | Afternoon reception |  |  | 2026-10-05 | 2 | 16 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-library-0 | vol-6 | Kenji Mori | shift-2026-10-05-library | Library welcome |  |  | 2026-10-05 | 2 | 15 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-05-library-1 | vol-7 | Yuki Nakamura | shift-2026-10-05-library | Library welcome |  |  | 2026-10-05 | 2 | 16 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-welcome-0 | vol-7 | Yuki Nakamura | shift-2026-10-06-welcome | Morning welcome |  |  | 2026-10-06 | 3 | 14 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-welcome-1 | vol-8 | Sofia Garcia | shift-2026-10-06-welcome | Morning welcome |  |  | 2026-10-06 | 3 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-welcome-2 | vol-9 | Ren Ito | shift-2026-10-06-welcome | Morning welcome |  |  | 2026-10-06 | 3 | 16 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-guidance-0 | vol-10 | Hana Kobayashi | shift-2026-10-06-guidance | Outpatient guidance |  |  | 2026-10-06 | 2.5 | 14 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-guidance-1 | vol-11 | Oliver Park | shift-2026-10-06-guidance | Outpatient guidance |  |  | 2026-10-06 | 2.5 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-afternoon-0 | vol-1 | Aiko Tanaka | shift-2026-10-06-afternoon | Afternoon reception |  |  | 2026-10-06 | 2 | 14 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-06-afternoon-1 | vol-2 | Daniel Kim | shift-2026-10-06-afternoon | Afternoon reception |  |  | 2026-10-06 | 2 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-welcome-0 | vol-4 | Haruto Suzuki | shift-2026-10-07-welcome | Morning welcome |  |  | 2026-10-07 | 3 | 13 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-welcome-1 | vol-5 | Maya Chen | shift-2026-10-07-welcome | Morning welcome |  |  | 2026-10-07 | 3 | 14 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-welcome-2 | vol-6 | Kenji Mori | shift-2026-10-07-welcome | Morning welcome |  |  | 2026-10-07 | 3 | 15 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-guidance-0 | vol-7 | Yuki Nakamura | shift-2026-10-07-guidance | Outpatient guidance |  |  | 2026-10-07 | 2.5 | 13 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-guidance-1 | vol-8 | Sofia Garcia | shift-2026-10-07-guidance | Outpatient guidance |  |  | 2026-10-07 | 2.5 | 14 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-afternoon-0 | vol-10 | Hana Kobayashi | shift-2026-10-07-afternoon | Afternoon reception |  |  | 2026-10-07 | 2 | 13 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-afternoon-1 | vol-11 | Oliver Park | shift-2026-10-07-afternoon | Afternoon reception |  |  | 2026-10-07 | 2 | 14 | Visitor guidance | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-library-0 | vol-12 | Mei Watanabe | shift-2026-10-07-library | Library welcome |  |  | 2026-10-07 | 2 | 13 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
record-2026-10-07-library-1 | vol-1 | Aiko Tanaka | shift-2026-10-07-library | Library welcome |  |  | 2026-10-07 | 2 | 14 | Library support | Synthetic service totals; no patient details. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Support requests
守織 SHUORI · Support requests
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Record ID | Title | Category | Priority | Status | Owner | Department | Due date | Description | Resolution | Version | Created (JST) | Updated (JST)
request-1 | Improve the first-visit route card | improvement | normal | in_progress | Operations team | Outpatient reception | 2026-10-13 | Review contrast and readability of the draft guidance card with reception staff. |  | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
request-2 | Coordinate orientation health reminders | coordination | high | open | Volunteer coordinator | Medical Administration | 2026-10-10 | Arrange private administrative reminders for upcoming clearance reviews. Keep clinical details in the approved hospital system. |  | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
request-3 | Volunteer availability consultation | consultation | normal | open | Volunteer office | Volunteer services | 2026-10-12 | Discuss a change in preferred activity hours and update the volunteer schedule after agreement. |  | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
request-4 | Library supply request completed | coordination | low | resolved | Library team | Patient Services | 2026-10-06 | Refresh book covers and circulation labels. | Supplies checked and delivered to the library team. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Resources
守織 SHUORI · Resources
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Record ID | Resource | Category | Location ID | Service location | Floor | Total quantity | Available quantity | Last inspection | Status | Administrative notes | Version | Created (JST) | Updated (JST)
resource-1 | Guidance boards | Wayfinding | reception | Reception & wayfinding | 1F | 8 | 6 | 2026-10-06 | ready | Confirm displayed routes before each shift. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
resource-2 | Volunteer identification vests | Volunteer supplies | coordination | Volunteer coordination | 1F | 24 | 18 | 2026-10-07 | ready | Clean supplies available at the briefing point. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
resource-3 | Library book carts | Library supplies | library | Library | 6F | 3 | 2 | 2026-10-05 | ready | One cart is reserved by the library team. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
resource-4 | Portable event display | Event supplies | coordination | Volunteer coordination | 1F | 2 | 0 | 2026-10-07 | maintenance | Inspection requested before the appreciation gathering. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
resource-5 | Visitor support wheelchairs | Mobility support | entrance | Main entrance | 1F | 6 | 4 | 2026-10-08 | ready | Illustrative inventory. Use only after training and local approval. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Scenarios
守織 SHUORI · Scenarios
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
No matching records. Column headers are retained. Spatial studies are independent of the operational roster. Coordinates are illustrative floor-local units.
Record ID | Scenario | Description | Object overrides | Added objects | Rehearsal routes | Version | Created (JST) | Updated (JST)

## Scene object overrides
守織 SHUORI · Scene object overrides
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
No matching records. Column headers are retained.
Scenario ID | Scenario | Object ID | Local X | Local height | Local Z | Rotation (radians) | Hidden

## Scene additions
守織 SHUORI · Scene additions
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
No matching records. Column headers are retained.
Scenario ID | Scenario | Added object ID | Object name | Asset kind | Floor | Local X | Local height | Local Z | Rotation (radians)

## Scene routes
守織 SHUORI · Scene routes
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
No matching records. Column headers are retained. Illustrative floor-local rehearsal. A round trip is 24 simulation minutes; no collision detection, measured walking speed or cross-floor routing.
Scenario ID | Scenario | Route ID | Volunteer ID | Volunteer | Shift ID | Shift | Floor | Waypoints

## Route points
守織 SHUORI · Route points
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
No matching records. Column headers are retained.
Scenario ID | Scenario | Route ID | Point sequence | Local X | Local Z

## Event types
守織 SHUORI · Event types
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Custom event classifications and module defaults. A type does not grant additional access permissions.
Record ID | Type name | Description | Display color | Default modules | Active | Version | Created (JST) | Updated (JST)
event-type-meeting | Team meeting | Briefings, planning and retrospective conversations. | blue | meeting checklist | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
event-type-training | Training & orientation | Learning sessions with attendance and preparation. | purple | attendance checklist | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
event-type-activity | Community activity | Volunteer-led activities linked to projects and resources. | green | attendance checklist | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
event-type-review | Follow-up & review | Administrative reviews and one-to-one support. | amber | checklist | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Events
守織 SHUORI · Events
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Tokyo civil dates and times. Meeting passcodes and URL query/fragment data are excluded; use the event in SHUORI for its complete join link. Attendance does not create service hours.
Record ID | Title | Event type ID | Event type | Date | End date | Start (JST) | End (JST) | Status | Owner | Description | Location ID | Service location | Floor | Venue or access details | Project ID | Project | Enabled modules | Meeting provider | Meeting address (without query) | Meeting ID (text) | Meeting agenda | Accessibility arrangements [field-accessibility] | Version | Created (JST) | Updated (JST)
event-briefing | Welcome team planning circle | event-type-meeting | Team meeting | 2026-10-08 | 2026-10-08 | 15:30 | 16:15 | confirmed | Volunteer coordinator | Synthetic demonstration event. Confirm arrangements before operational use. | coordination | Volunteer coordination | 1F | Volunteer briefing point | project-welcome | A warmer first visit | meeting checklist | zoom |  |  | Review the welcome pilot, share observations and agree the next improvement. |  | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
event-orientation | New volunteer orientation | event-type-training | Training & orientation | 2026-10-10 | 2026-10-10 | 10:00 | 12:00 | draft | Volunteer coordinator | Synthetic demonstration event. Confirm arrangements before operational use. | coordination | Volunteer coordination | 1F | Volunteer briefing point | project-onboarding | Ready to help: orientation | attendance checklist | other |  |  |  | Offer a written agenda and step-free access. Confirm individual requests privately. | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
event-library | Reading programme preparation | event-type-activity | Community activity | 2026-10-12 | 2026-10-12 | 13:00 | 14:00 | draft | Volunteer coordinator | Synthetic demonstration event. Confirm arrangements before operational use. | library | Library | 6F | Library | project-library | Stories that connect | attendance checklist | other |  |  |  |  | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Event attendance
守織 SHUORI · Event attendance
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Recorded invitation, confirmation and attendance states. Assigned participants without an attendance entry remain in Event relationships.
Event ID | Event | Volunteer ID | Volunteer | Attendance status | Attendance notes
event-orientation | New volunteer orientation | vol-15 | Nora Hayashi | confirmed
event-orientation | New volunteer orientation | vol-16 | Kai Takahashi | invited
event-library | Reading programme preparation | vol-2 | Daniel Kim | invited
event-library | Reading programme preparation | vol-8 | Sofia Garcia | invited

## Event checklist
守織 SHUORI · Event checklist
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Dates are Tokyo civil dates. User-entered text is stored as text. No rows are omitted silently.
Event ID | Event | Checklist item ID | Title | Complete | Owner | Due date
event-briefing | Welcome team planning circle | briefing-agenda | Prepare the anonymous feedback summary | TRUE | Operations team | 2026-10-08
event-briefing | Welcome team planning circle | briefing-notes | Upload meeting notes and next actions | FALSE | Volunteer coordinator | 2026-10-09
event-orientation | New volunteer orientation | orientation-materials | Prepare orientation materials | FALSE | Volunteer office | 2026-10-09

## Event relationships
守織 SHUORI · Event relationships
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Explicit links to participants, shifts, resources and project. A resource link is a planning reference, not an inventory reservation.
Event ID | Event | Linked collection | Linked record ID | Linked record
event-briefing | Welcome team planning circle | volunteers | vol-1 | Aiko Tanaka
event-briefing | Welcome team planning circle | volunteers | vol-2 | Daniel Kim
event-briefing | Welcome team planning circle | volunteers | vol-3 | Emi Sato
event-briefing | Welcome team planning circle | projects | project-welcome | A warmer first visit
event-orientation | New volunteer orientation | volunteers | vol-15 | Nora Hayashi
event-orientation | New volunteer orientation | volunteers | vol-16 | Kai Takahashi
event-orientation | New volunteer orientation | resources | resource-2 | Volunteer identification vests
event-orientation | New volunteer orientation | projects | project-onboarding | Ready to help: orientation
event-library | Reading programme preparation | volunteers | vol-2 | Daniel Kim
event-library | Reading programme preparation | volunteers | vol-8 | Sofia Garcia
event-library | Reading programme preparation | resources | resource-3 | Library book carts
event-library | Reading programme preparation | projects | project-library | Stories that connect

## Journal entries
守織 SHUORI · Journal entries
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Flexible journal and follow-up records. These entries are not counted as service hours; activity records remain the source for hours and interactions.
Record ID | Title | Category | Status | Date | Follow-up date | Volunteer ID | Volunteer | Event ID | Event | Record body | Follow-up agreed [field-review-agreed] | Version | Created (JST) | Updated (JST)
entry-orientation | Orientation preparation check-in | Onboarding | open | 2026-10-08 | 2026-10-10 | vol-15 | Nora Hayashi | event-orientation | New volunteer orientation | Synthetic note: send the session agenda and confirm the preferred contact method. No clinical details. | TRUE | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
entry-appreciation | Welcome desk contribution recognised | Recognition | complete | 2026-10-06 |  | vol-2 | Daniel Kim |  |  | Synthetic note: thanked the volunteer for helping refine the first-visit guidance card. |  | 1 | 2026-10-08 17:53 | 2026-10-08 17:53

## Files and links
守織 SHUORI · Files and links
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
No matching records. Column headers are retained. Metadata only: file bytes, physical storage paths and credentials are excluded. File download paths require a signed-in session on the originating SHUORI installation. External URLs remain literal text and retain their saved query parameters.
Record ID | Parent collection | Parent record ID | Parent record | File or link name | Storage kind | External URL (text) | Authenticated download path | Content type | Size (bytes) | SHA-256 | Uploaded by | Description | Version | Created (JST) | Updated (JST)

## Locations
守織 SHUORI · Locations
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Coordinates and capacity are illustrative planning assumptions, not surveyed dimensions or approved capacity limits.
Record ID | Location | Floor | Building | Scene X | Scene Z | Planning capacity | Reference provenance | Source and planning notes
entrance | Main entrance | 1F | Outpatient Building | -10 | 8 | 4 | concept | Illustrative welcome station near the outpatient entrance. Position and capacity are planning assumptions.
reception | Reception & wayfinding | 1F | Outpatient Building | 0 | 5 | 4 | concept | Illustrative reception support station. Verify the operational desk with hospital staff.
outpatient | Outpatient support | 1F | Outpatient Building | 8 | -3 | 4 | concept | Conceptual volunteer meeting point for outpatient guidance; not a verified clinic position.
library | Library | 6F | Central Clinical Building 2 | -7 | -5 | 3 | concept | Illustrative library station in the demonstration model. Names, coordinates and capacity are examples; confirm the local library location and opening hours before scheduling.
garden | Courtyard activity station | 1F | Concept activity zone | 10 | 9 | 6 | concept | Proposed event station for simulation only; operational approval and a site check are required.
coordination | Volunteer coordination | 1F | Concept operations zone | -9 | -8 | 4 | concept | Illustrative volunteer briefing point; not an official hospital office location.

## Field dictionary
守織 SHUORI · Field dictionary
Generated 2026-10-08 18:03:47 JST · Asia/Tokyo · demo · version 1.4.0
workspace ¦ All records in the stated scope ¦ View label: All saved operational collections
Custom columns retain stable field IDs, labels and native value types. Archived definitions and existing values remain exportable. An empty selected scope includes headers only.
Record ID | Applies to | Field label | Value type | Select options | Required | Active | Display order | Definition status | Version | Created (JST) | Updated (JST)
field-preferred-role | volunteers | Preferred contribution | select | Welcome desk Library programme Event support Behind the scenes | FALSE | TRUE | 0 | Registered field | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
field-accessibility | events | Accessibility arrangements | textarea |  | FALSE | TRUE | 0 | Registered field | 1 | 2026-10-08 17:53 | 2026-10-08 17:53
field-review-agreed | entries | Follow-up agreed | boolean |  | FALSE | TRUE | 0 | Registered field | 1 | 2026-10-08 17:53 | 2026-10-08 17:53